## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Afza Fathima | 2026-09-01 | DOCX resumes that place sections inside tables returned incomplete text, so skills/experience in those sections were not parsed. | Sprint 1 | Afza Fathima | Logical | Changed DOCX extraction to read paragraphs and table cells in document order; merged cells de-duplicated (text_extraction.py). | 2026-09-02 | Closed | Verified with a table-layout sample resume. Severity: High.
2 | Afza Fathima | 2026-09-07 | Skill extraction matched the English words 'go' and 'r' as the Go and R programming languages (false positives in internship dataset). | Sprint 2 | Afza Fathima | Logical | Removed 'Go' and 'R' from skill_vocabulary after confirming every sample match was a false positive. | 2026-09-08 | Closed | Known trade-off: real Go/R postings are no longer detected. Severity: Medium.
3 | Afza Fathima | 2026-09-10 | Near-identical reposts of the same posting (e.g. 'Digital Marketing Intern' at one company) passed exact-match de-duplication and appeared twice in search results. | Sprint 2 | Afza Fathima | Logical | Added near-duplicate detection (word-set Jaccard > 0.85 within company) to build_dataset.py; 63 reposts removed and dataset rebuilt. | 2026-09-11 | Closed | Dataset remains 200 postings after the fix. Severity: Medium.
4 | Afza Fathima | 2026-09-10 | Company name extracted for only 97 of 200 postings (48.5%); the rest are shown as 'Undisclosed Company'. | Sprint 2 | Afza Fathima | Others | Root cause analysed: 21 postings have no company text, 82 use patterns the regexes do not catch. Accepted as a known limitation for this release. | 2026-09-10 | Open | Does not affect matching or RAG (they use skills/description). A NER model would be needed. Severity: Low.
5 | Afza Fathima | 2026-09-14 | TF-IDF retrieval can rank an irrelevant posting first: 'frontend React developer' returns 'Business Operations Intern for Social Impact' ('react' / 'development' used in a different sense). | Sprint 2 | Afza Fathima | Logical | Root cause analysed (keyword overlap cannot separate word senses). Sentence-Transformers backend implemented behind EMBEDDING_BACKEND but not yet validated on a machine with internet access. | 2026-09-16 | Open | Re-verified on final build: the relevant posting still appears at rank 3. Fix = validate and enable the semantic backend (US18). Severity: Medium.
6 | Afza Fathima | 2026-09-15 | Evaluation helper is_relevant() only checked title/industry/function, under-counting precision@5 (84%) because valid matches had generic titles (BI Interns, 'Intern'). | Sprint 2 | Afza Fathima | Logical | Evaluation now also checks extracted skill lists (precision@5 = 96%); remaining 'BI Interns' case traced to missing 'tableau' keyword in the evaluation list. | 2026-09-16 | Closed | Effective precision@5 is 100% for all 5 profiles once the evaluation keyword gap is accounted for. Severity: Low.
7 | Afza Fathima | 2026-09-16 | Postings whose requirements are unpunctuated bullet lists (e.g. Graphic Designer) are treated as one sentence; the word 'bonus' makes required skills (Photoshop, Illustrator, InDesign) count as preferred. | Sprint 2 | Afza Fathima | Logical | Root cause analysed (sentence splitter relies on . ! ?). Needs bullet-aware segmentation; added to backlog as US41. | 2026-09-16 | Open | Postings still retrieved; match score is lower than it should be and the 'missing required skills' text can mislead. Severity: Low.
8 | Afza Fathima | 2026-09-20 | Certifications and completed online courses were never extracted or stored, so the Skill Gap agent could not compare them. | Sprint 3 | Afza Fathima | Logical | Added Certification model, extended the parser prompt and added a safety-net module (certifications.py) that normalises entries and scans certificate-style headings. | 2026-09-22 | Closed | Unit tested with string, dict, blank and duplicate entries. Severity: Medium.
9 | Afza Fathima | 2026-10-03 | Matching Agent lists TypeScript as fully missing while the Skill Gap Agent reports it as partially demonstrated (student has JavaScript) - the two screens contradict each other. | Sprint 4 | Afza Fathima | Logical | Added related-skill (SKILL_FAMILIES) partial credit to score_skills in matching_agent.py and re-ran evaluation and E2E tests. | 2026-10-05 | Closed | Verified: JavaScript vs required TypeScript now returns 'partially matched' with half credit. Severity: Medium.
10 | Afza Fathima | 2026-10-04 | E2E conversation test crashed: the interview_prep_summary intent makes a third, unmocked LLM call (interview_agent.get_client). | Sprint 4 | Afza Fathima | Others | Mocked interview_agent.get_client in test_conversation_context.py and documented it in the M4.2 report. | 2026-10-04 | Closed | Test defect, not a product defect. Severity: Low.
11 | Afza Fathima | 2026-10-04 | Job context in the assistant is 'sticky': a later generic question is stored with the previous referenced_job_id. | Sprint 4 | Afza Fathima | Logical | Checked impact: replies are not affected (general questions run a fresh search). Only history bookkeeping is mislabelled; fix deferred. | 2026-10-04 | Open | Cosmetic unless chat history is ever grouped by job. Severity: Low.
12 | Afza Fathima | 2026-10-05 | Existing career.db files had no conversation_id column after the multi-chat feature, so old installs failed on chat. | Sprint 4 | Afza Fathima | Logical | Added run_migrations(): idempotent ALTER TABLE + index, and old messages are moved into an 'Earlier chat' per student. | 2026-10-06 | Closed | Runs safely on every start. Severity: High.
13 | Afza Fathima | 2026-10-07 | Education matching ignores common degree names: 'B.Tech', 'Bachelor of Technology', 'Bachelor of Engineering' and 'Master of Science' are scored as no degree (education score 40) against 'Bachelor's degree' / 'Master's degree' requirements. Same logic in skill_gap_agent.assess_education_gap. | Sprint 4 | Afza Fathima | Logical | Reproduced in unit test UT-MAT-07. Root cause: the code looks for the first word of the level name ("bachelor's", with apostrophe) inside the degree text. Fix added to backlog (US44). | 2026-10-07 | Open | Lowers overall match score by 12 points for typical Indian B.Tech students. Severity: High.
14 | Afza Fathima | 2026-10-07 | Hallucination check misses an invented skill when it is the last word of a sentence: 'Built apps with React and Docker.' is reported clean because the tokenizer keeps the full stop ('docker.') and it does not match the skill vocabulary. | Sprint 4 | Afza Fathima | Logical | Reproduced in unit test UT-CUS-04. Fix: strip trailing punctuation when tokenising in customization_agent._keywords (keep dots inside names like node.js). | 2026-10-07 | Open | Weakens the 'no invented skills' guarantee for generated resumes/cover letters. Severity: High.
15 | Afza Fathima | 2026-10-07 | Skill score can never reach 100: when a posting lists no preferred skills the 20% preferred weight scores 0, so a perfect required-skill match gives skill score 80 and overall 88. | Sprint 4 | Afza Fathima | Logical | Reproduced in unit test UT-MAT-01 (2 of 2 required skills -> score 80). Fix: redistribute the weight to required skills when no preferred skills exist. | 2026-10-07 | Open | Ranking order is still correct; absolute scores are understated. Severity: Medium.
16 | Afza Fathima | 2026-10-07 | e2e_tests/test_rag_retrieval.py asserts exact titles such as 'Frontend Intern' that do not exist in the 200-posting dataset; as shipped it reports 0/5 top-1 and fails its own assertion (the M4.2 report records 5/5). | Sprint 4 | Afza Fathima | Standards | Verified by re-running the test. Update the test to assert topical relevance (skills/keywords) instead of exact titles and re-run before submission. | 2026-10-07 | Open | Retrieved results are mostly topical (e.g. 'Social Media & Digital Marketing Internship' for the marketing query). Severity: Medium.
17 | Afza Fathima | 2026-10-07 | build_dataset.py and the E2E tests use hard-coded absolute Linux paths (/home/claude/..., /tmp/e2e_resume.pdf), so they cannot be re-run on a Windows/PowerShell machine as the setup guide implies. | Sprint 4 | Afza Fathima | Standards | Logged. Replace with pathlib-relative paths and tempfile. | 2026-10-07 | Open | Does not affect the running application. Severity: Medium.
18 | Afza Fathima | 2026-10-07 | Login page shows a Password field and 'Forgot password?', but the backend never stores or checks a password - anyone who knows an email can open that account. | Sprint 4 | Afza Fathima | Logical | Logged as a security limitation for this release; real authentication added to the backlog (US42, Won't Have). | 2026-10-07 | Open | Acceptable for a local demo only. Severity: High for any real deployment.
19 | Afza Fathima | 2026-10-07 | Settings notification toggles (email alerts, match alerts, weekly digest) only change local React state; they are not saved and no alerts exist. | Sprint 4 | Afza Fathima | User Interface | Logged; persistence and alerts added to backlog (US43, Won't Have). | 2026-10-07 | Open | UI suggests a feature that is not implemented. Severity: Low.
20 | Afza Fathima | 2026-10-07 | Resume upload trusts the client-supplied Content-Type header; the file signature is not checked. | Sprint 4 | Afza Fathima | Others | Logged. Add magic-byte check (%PDF / PK zip) in routers/resumes.py. | 2026-10-07 | Open | Mitigated by 5 MB limit, uuid file names and extraction in a parser, not execution. Severity: Low.
21 | Afza Fathima | 2026-10-08 | requirements.txt lists SQLAlchemy twice (unpinned 'sqlalchemy' and 'SQLAlchemy==2.0.45') and leaves most packages unpinned. | Sprint 4 | Afza Fathima | Standards | Logged. Keep a single pinned entry per package. | 2026-10-08 | Open | Install works today; builds may differ over time. Severity: Low.
22 | Afza Fathima | 2026-10-08 | frontend/README.md is still the default Vite template and frontend/SETUP.md describes only the first five pages as placeholders, although the app now has ten pages. | Sprint 4 | Afza Fathima | Maintainability | Logged. Rewrite both documents to match the final app. | 2026-10-08 | Open | Documentation only. Severity: Low.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others